## Sheet1
Location | Network | Protection/ Relocation | Impact Rating
Alison Road Break-Off |  | Telstra Network Impacted by Route M at this location
Alison Road and Doncaster Avenue Intersection | 6 xA100 & 1.2x1.2 manhole | Approx 1150 cover to Alison Rd Road crossing. Re-align track slab west to clear manhole No impact. Otherwise Major impact requiring new road crossing of Alison Rd + manhole and 150m x 6 way east. Possible conduit upgrade outside this area for cutover of 12 x OF cables will be required. | High
Doncaster Avenue South East along Alison Road to Darley Road- Randwick Racecourse | 6 x E85x 420m & 3 off 1.2x1.2 manholes , 2 off 1.8x1.2 manholes, 6 8 & 9 pits PLUS all 5 conduit feeds into the Racecourse from Alison Road | Will require relocation of around 450m of conduit & manholes and pits plus new entries into Racecourse. No details on LR turnout area across footpath east of Doncaster Ave (advised 3/12/13). Likely complete relocation to northern side of Alison Road with new cable feeds across Rd into Racecourse buildings | High
Road Crossing of Alison Road into Racecourse property | 2xP100 x 40m | Included with above
LR crossing of footpath Darly Rd to around Cowper St | Empty appear abandoned 6 X E85 requires confirmation of exact length remaining in footpath | Appear to be unuseable by Telstra due to age and condition | Moderate
Wansey Road Stop Location Changed Potential Impact Remains | P50 & P100 x 170m plus pits@ approx 50m | Wansey Road Stop built over footpath. Relocate to east side of Wansey Rd and new road crossing of Wansey Road and 2 new lead-ins to Racecourse | Major
Wansey Road & High Street Stop | P50x150m, 1xA100 Rd crossing x 25m, 1xA100 x50m plus pits | Relocate to east side of Wansey Road and new Road crossing of Wansey Rd | Significant
Botany Street and High Street Intersection & West | 1xA100 Rd crossing x20m | Relocate Rd Crossing | Moderate
High Street Road Crossing at Botany Street | 1xA100 Rd crossing x20m | Relocate Rd Crossing | Significant
Clara Street and High Street Intersection | 2xA100 Rd crossing x20m | Relocate Rd Crossing | Significant
Avoca Street and High Street Intersection | 2 x A100 & 4 x E85 x 40m & 1.2x1.2 congested manhole |  | High
Belmore Road Crossing | P50 x20m | Possible no impact | TBC
North east corner of Alison Rd & Anzac Pde | 4 xA100 & 6 x A100 & 1.2x1.2 manhole | Relocate over 120 metres. 4 -OF joint-joint + new manhole | High
Tay St & Anzac Pde | 12xA100 | Assesed cover 1200. TBC by slit trench. Likely Protection | TBC
Tay St splay to Anzac Pde | Shared Pole Distribution | 4m from edge of track slab, OH power may impact | TBC
Todman Ave & Anzac Pde North | 12xP100 | Assesed cover 800-950. TBC by slit trench. Likely Protection | High
Todman Ave & Anzac Pde South | 3xA100 | Assesed cover 700-830. TBC by slit trench. Marginal for Protection | Major
High Street Stop Location Changed No Impact | 6 + 2 way & 1.2x1.2 manhole | Relocate over 250 metres, 2 -OF joint-joint + new manhole. | High
Day Avenue and Anzac Parade Intersection | 3 x A100 | Assesed cover approx 600, TBC by slit trench. Likely relocate Rd Xing and joint-joint c/over of OF | Major
Barker St and Anzac Parade Intersection | G50 | Assesed cover approx 600-700, TBC by slit trench. Likely relocate Rd Xing due to condition of Steel pipe | Moderate
Harbourne Lane and Anzac Parade Intersection | P50 | Assesed cover approx 450-500, TBC by slit trench. Relocate Rd Xing | Moderate
Strachan Street / Middle Street and Anzac Parade Intersection | E100 | Assesed cover approx 400-500, TBC by slit trench. Relocate Rd Xing | Major
Borodale Road / Meeks Street and Anzac Parade Intersection | P100 | Assesed cover approx 500, TBC by slit trench. Relocate Rd Xing | Moderate
Anzac Parade Road Crossing @ Kingsford Stop | 12x A100 | Assesed cover approx 1000, TBC by slit trench. Likely protection of Rd Xing. TBC by slit trenching | Moderate
Devonshire, Chalmers & Randle Streets | Local cable in area | No impact | Nil
Elizabeth Street west side | empty A100 | Relocate | Moderate
Elizabeth Street east side | 28xP100 | Conduits deep across Track protection, TBC by slit trenching | TBC
Elizabeth & Devonshire Streets north east corner | P100, P50 & P20 x 50m & pits | Potential impact on corner (Dynamic Envelope) | TBC
Elizabeth to Riley street south side of Devonshire To Devonshire Street Stop | 3 x1.2x1.2, 1 x2.4x1.2 & 1x1.8x1.2 manholes, 4xA100 & 4 pits | Potential impact from LR Dynamic Envelope on Telstra network along narrow footpath on south side of Devonshire Street x approx 400m | High
Waterloo Street Road Crossing | 4xA100 | Relocate road crossing concurrent with above item, protection / relocation. TBC by slit trenching | High
Riley Street (west) Road crossing @ Devonshire Street Stop | 0.9x1.2 manhole 2xA100 x35m | Relocate road crossing concurrent with above protection / relocation | Major
Riley Street (centre line) Road crossing @ Devonshire Street Stop | 12xP100 x50m | Protection lowering of conduits if possible (May be concrete encased) manhole requires pumping out to determine detail. TBC by slit trenching | High
Wiltshire Street Road Crossing | E100 & A100 x20m | Relocate Road crossing | Major
Nickson Lane Road Crossing | Old Empty E100 & P100 x20m | Relocate Road crossing | Moderate
Bourke Street Road Crossing (west side) | 3xA100 x110m, 2xP100 x25m | Relocate Road crossings and Intercept 3 x A100 and build new manhole for cutover | Major
Bourke Street Road Crossing (east side) | P50 x50m + pits | Relocate existing conduit and pits in footpath at track crossing | Moderate
Olivia Lane west side of Olivia Gardens | P100 x50m + pits | Service will be removed with demolition of Olivia Gardens. Relocate & retain P100 crossing of track with suitable cover | Moderate
Parham Place east side of Olivia Gardens | A100 x50m + pits | Relocate & retain P50 crossing of track with suitable cover | Moderate
South Dowling Street footpath west side | 2xA100 x90m + pits | Relocate within footpath area | Moderate
Anzac Parade west footpath @ More Park | 2xE85 x100m | Possible protection @tunnel portal / relocate large size OF over joint lengths old conduits present - potential for extensive new conduit installation | High
Anzac Parade west footpath @ More Park | Direct Buried cable | Relocate over tunnel construction | Moderate
Lang Road south side Fox Studio Feed | 4xP100 | Possible protection @ track crossing or relocate 4 way with new manhole. Vacant conduit required joint to joint for cutover | Major
65m South of Lang Road | P50 x50m + pits | Relocate over 50m | Moderate
South of Lang Road | P50 x18m + pits | Under track Relocate over 180m | Moderate
West end Robertson Road @ BusWay | P50x30m | Under track Relocate over 300m | Moderate
West end Robertson Road Crossing of BusWay | 2xE85 x50m + manholes | Relocate over 50m | Significant
Alfred Street @ Circular Quay Stop north side Route F | 2xA100 Stubbed at kerb | Nil
Alfred Street @ Circular Quay Stop south side Route E | 2xA100 x150m+ pits | Relocate between Pitt and Loftus Streets x 150m with new lead-ins to street vendors | High
Pitt Street east, crossing track, Alfred St Route D | 2xA100 x50m+ pits | Relocate across Alfred x 50m +manhole and extension for OF cutover | Major
Pitt Street west, crossing track, Alfred St Route C | 20xP100 | Protect appear to have sufficient cover, TBC by Slit Trenching | TBC
Pitt Street west, crossing track, Alfred St Route B | 6xA100 + 8xP100 x40m | Possible protection dependant on cover relocate, large number of OF over joint lengths old conduits present - potential for extensive new conduit installation. TBC by Slit Trenching | High
George Street east side crossing track, Alfred St Route A | 4 x P100 + 8 x A100 (active) 6 x A100 + 10 x G50 (empty) | Possible protection dependant on cover relocate, large number of OF over joint lengths old conduits present - potential for extensive new conduit installation. TBC by Slit Trenching | High
Essex Street North Road Crossing | 6xP100 x 20m | Possible protection dependant on cover relocate, large number of OF over joint lengths if relocation required. TBC by Slit Trenching | High
Essex Street South Road Crossing | 2 xG80 CPR | No evidence of Rd Xing | Nil
Road Crossing @ Grosvener Place Building Entry | 6xP100 x 50m + manhole | Possible protection dependant on cover relocate, large number of OF over joint lengths if relocation required. TBC by Slit Trenching | High
Dalley Tunnel Road Crossing @ Grosvener Street | Tunnel Structure | Appears sufficient cover for protection , confirm by slit trenching | TBC
Jamison Street Road Crossing | 8 x P100 x 25m | Appears sufficient cover for protection, confirm by slit trenching | TBC
Margaret Street Road Crossing | 6 x E85 x 50m, 3xA100 unable to be located may be redundant | E85 conduits appear to have sufficient cover for protection, confirm by slit trenching. 3 x A100 Vacant unknown at this stage. TBC by Slit Trenching | TBC
Hunter Street Road Crossing | 2 x G80 x20m | Potential impact may be able to protect GI pipes dependant on condition, confirm by slit trenching | Major
Road Crossing between 309 and 316 George Street | P100 x 75m | Unable to locate Referred to UUS, located entry to CBA building on west side of George St. Assumed NO Rd crossing at this location | TBC Nil
Wynyard Stop encroachment on western footpath of George Street | 4xP100 x 50m | Detail of encroachment to be confirmed manholes located 2m from kerb | TBC
Martin Place (north) Tunnel Road Crossing @ Barrack Street | Tunnel Structure | Appears sufficient cover for protection , confirm by slit trenching | TBC
Martin Place (south) Tunnel Road Crossing to old GPO Building | Tunnel Structure | Marginal cover for Track slab, potential Heritage issues, confirm cover by slit trenching | TBC
King Street Road Crossing | 6xP100 x 50m | Appears sufficient cover for protection, confirm by slit trenching | TBC
Park Street Road Crossing | 33xP100 | Assumed conduits are contained within the ceiling space of Town Hall Station | TBC
Park Street Road Crossing | 4x100x30m | Min cover 250-150 cover over Town Hall Station structure | Significant
Bathurst Street Road Crossing | 4xP100 + 4xP100 +12xP100, 12 Way Unknown | 4 XP100 likely impact, 4 x P100 800pr+3xOF likely impact 12xP100 2x5200,1800, 400Pr +23xOF. All cover to be confirmed by slit trenching | High
Tunnel Road Crossing @ Liverpool Street | Tunnel Structure | Appears sufficient cover for protection , confirm by slit trenching | TBC
Goulburn Street Road Crossing | 4xP100 x30m | crossing impacted slit trenching 450 cover Relocate. | Major
Tunnel Road Crossing @ Campbell Street | Tunnel Structure | Cover approx 300 Track design solution required due to space limitation in Tunnel | High
Tunnel Road Crossing @ Hay Street for Hay Street turnout west | Tunnel Structure | Appears sufficient cover for protection , confirm by slit trenching | TBC
Tunnel Diagonal Road Crossing @ Barlow Street | Tunnel Structure | Appears sufficient cover for protection , confirm by slit trenching, may be too deep to locate | TBC
Rawson Place Road Crossing on East side of George Street | 4xP100 x70m | Relocate between Barlow and Rawson Place x 70m confirm cover by slit trenching | Major
Rawson Place Road Crossing west side of Pitt | 3xA100 x60m | Relocate between existing manholes x 60m confirm cover by slit trenching | Major
Secondary Tunnel Structure Rawson Place & Pitt Street Diagonal Tunnel Crossing | Tunnel Structure | Assumed sufficient cover for protection, confirm cover by slit trenching | TBC
Main Tunnel Structure along centre of Pitt Street Crossing Rawson Place | Tunnel Structure | Assumed sufficient cover for protection, confirm cover by slit trenching | TBC