## Cover
Proposed ADSL Enabled Exchanges
Issue 388
2019-08-22
The report is updated on an as needs basis. In general, an entry for a particular ESA will stay on this report for 3 months after enablement.
This report is a list of exchanges and sub exchanges proposed for internet grade ADSL enablement.
This report will be updated when there are further Exchange Service Areas to be ADSL Enabled.
Notes:-
Proposed dates are indicative only and may vary.
Alll services within an ESA may not be ADSL capable. Only a Full Service Qualification will confirm whether ADSL can be provided.

## Proposed ADSL ESAs
Proposed ADSL Exchange Service Areas
Issue 388
2019-08-22
This and other DSL Reports and Plans can be found at:
http://telstrawholesale.com.au/products/broadband/adsl/adsl-reports-plans/index.htm
© Telstra Corporation Limited 2013.
State | CCA | ESA Code | ESA Name | Area Code | Range from | Range to | Full Range | Classification | ADSL Proposed Date | ADSL Completed Date | ADSL 2+ | Comment
QLD | CLONCURRY | MTIB | BARKLY | 7 | 74748 3000 | 74748 3299 | 74748 3000-3299 | Zone 3 | 2019-09-30 |  | YES | Alpurrurulam Exchange (ALPV01)
QLD | CLONCURRY | MTIB | BARKLY | 8 | 74748 4800 | 74748 4999 | 74748 4800-4999 | Zone 3 | 2019-09-30 |  | YES | Alpurrurulam Exchange (ALPV01)
QLD | HOPEVALE | HPVE | HOPEVALE | TBA | TBA | TBA | TBA | TBA | 2019-12-31 |  | YES | Hopevale Exchange (HPVE01)

## Record of Issues
Proposed ADSL Exchange Service Areas
Issue 388
2019-08-22
0
Record of Issues
Issue Number | Date | Nature of Amendment
303 | 2014-05-14 | No change
304 | 2014-05-21 | No change
305 | 2014-05-28 | No change
306 | 2014-06-04 | No change
307 | 2014-06-11 | No change
308 | 2014-06-18 | Added Millstream
309 | 2014-06-25 | No change
310 | 2014-07-02 | No change
311 | 2014-07-09 | Added Laharam North
312 | 2014-07-10 | No change
313 | 2014-09-03 | No change
314 | 2014-10-01 | Updated Laharam North and added Deans Marsh (DEMA)
315 | 2014-10-22 | No change
316 | 2014-11-04 | No change
317 | 2014-12-03 | Updated completed date for Deans Marsh (DEMA)
318 | 2014-12-24 | No change
319 | 2015-01-07 | No change
320 | 2015-02-04 | No change
321 | 2015-02-26 | No change
322 | 2015-03-26 | No change
323 | 2015-04-30 | No change
324 | 2015-05-14 | Added Callington ESA (CGTN)
325 | 2015-05-21 | Date amendment for CGTN
326 | 2015-06-11 | Added Nyabing (NYAB)
327 | 2015-06-25 | Added Cambrai (CMBR)
328 | 2015-07-23 | Added Indigo Valley (INDV), Winchelsea South (WINS) & Majorca (MAJO)
329 | 2015-07-30 | No change
330 | 2015-08-27 | No change
331 | 2015-09-10 | Updated NYAB and CGTN
332 | 2015-09-14 | Update classifications for CGTN, NYAB, CMBR, INDV, WINS, MAJO
333 | 2015-09-24 | Populated ADSL completion date for CMBR 16-Sep-15
334 | 2015-10-22 | Date update for WINS & MAJO
335 | 2015-11-05 | Date update for INDV
336 | 2015-11-26 | Added GNDY and BTGA
337 | 2015-12-21 | Update dates for BTGA
338 | 2016-01-28 | Update date for WINS
339 | 2016-03-03 | Update completeion date for GNDY
340 | 2016-03-31 | Update completion date for WINS and MAJO
341 | 2016-04-28 | No change
342 | 2016-05-26 | No change
343 | 2016-06-30 | Added Georgina (GINA) and Haddon (HADN)
344 | 2016-07-28 | No change
345 | 2016-08-04 | Added Stansbury (STRY)
346 | 2016-08-25 | Added number range for Stansbury (STRY)
347 | 2016-09-08 | Updated proposed dates for GINA, HADN and STRY
348 | 2016-10-14 | ADSL completed date added for Stansbury (STRY)
349 | 2016-10-27 | Updated CCA to Yorketown for Stansbury (STRY)
350 | 2016-11-17 | Added Davenport (DAVE) and Rodinga (RODG)
351 | 2016-11-24 | No change
352 | 2016-12-01 | Populated ADSL completion date for HADN
353 | 2016-12-20 | Added new ESA ADSL Enablement for AURN
354 | 2017-01-23 | Updated number range and dates for AURN
355 | 2017-02-23 | No updates this month
356 | 2017-03-23 | Updated date for Rodinga (RODG) to 31st Mar 2017
357 | 2017-04-20 | Added new ESA ADSL Enablement for BULS & SBRY. Entered ADSL completed date for Rodinga (RODG)
358 | 2017-05-18 | Date updates for BULS, AURN. Removed completion date for SBRY.
359 | 2017-06-01 | Updated completion dates for GINA and SBRY.
360 | 2017-06-15 | AURN date changed to 31st July as project EOT'd.
361 | 2017-06-29 | Updated completion dates for BULS.
362 | 2017-07-20 | No changes
363 | 2017-08-16 | Updated completion dates for AURN.
364 | 2017-09-21 | Removed records older than 3 months - HADN, STRY, DAVE, RODG, SBRY, GINA, BULS
365 | 2017-10-19 | No changes
366 | 2017-11-16 | No changes
367 | 2017-12-15 | Added new ADSL enablement for KWYA
368 | 2018-01-25 | No changes
369 | 2018-02-15 | No changes
370 | 2018-03-09 | No changes
371 | 2018-04-05 | No changes
372 | 2018-05-03 | No changes
373 | 2018-06-07 | Added new ADSL enablement for FGYN
374 | 2018-07-12 | Made changes to FGYN number range
375 | 2018-08-02 | Removed Kowanyama (KWYA)
376 | 2018-09-13 | No changes
377 | 2018-10-04 | No changes
378 | 2018-10-18 | No changes
379 | 2018-11-21 | Added Barkly ESA (MTIB)
380 | 2018-12-20 | Minor update to Barkly ESA (MTIB)
381 | 2019-01-24 | Removed Ferny Glen ESA (FGYN)
382 | 2019-02-21 | No changes
383 | 2019-03-21 | Removed Ferny Glen ESA (FGYN)
384 | 2019-05-09 | No changes
385 | 2019-06-06 | No changes
386 | 2019-06-20 | No changes
387 | 2019-07-26 | Completion date update for MTIB
388 | 2019-08-22 | No changes